## Sheet1
Project Name | Project Duration | Project start date | Project End date
E-Waste management | 34 | 2018-02-19 | 2018-03-25
Task Id | Task Description | Task Duration | Start Date | End Date | 2018-02-19 | feb 20,2018 | feb 21,2018 | feb 22,1018 | feb 23,2018 | feb 24,2018 | feb 25,2018 | feb 26,2018 | feb 27,2018 | feb 28,2018 | march 1,2018 | march 2,2018 | march 3,2018 | march 4,2018 | march 5,2018 | march 6,2018 | march 7,2018 | march 8,2018 | march 9,2018 | march 10,2018 | march 11,2018 | march 12,2018 | march 13,2018 | march 14,2018 | march 15,2018 | march 16,2018 | march 17,2018 | march 18,2018 | march 19,2018 | march 20,2018 | march 21,2018 | march 22,2018 | march 23,2018 | march 24,2018 | march 25,2018 | march 26,2018 | march 27,2018 | march 28,2018
1 | Meet up with the company who recycles plastic | 2 | 2018-02-19 | feb 20,2018 | X | X
2 | Collect the data | 6 | feb 21,2018 | feb 26,2018 |  |  | X | X | X | X | X | X
3 | Organize the data accordingly | 3 | feb 27,2018 | march 1,2018 | [8 empty] | X | X | X
4 | Analyze the data | 2 | march 2,2018 | march 3,2018 | [11 empty] | X | X | [16 empty] | X | X | X | X | X | X | X | X | X
5 | meeting with them and ask them which would be more suitable for them | 1 | march 4,2018 | march 4,2018 | [13 empty] | X
6 | Finalize the design | 1 | march 5,2018 | march 5,2018 | [14 empty] | X
7 | Create the wireframe | 3 | march 6,2018 | march 8,2018 | [15 empty] | X | X | X
8 | Designing | 5 | march 9,2018 | march 13,2018
9 | code for the application | 10 | march 14,2018 | march 23,2018 | [11 empty] | X | [11 empty] | X | X | X | X | X | X | X | X | X | X
10 | Testing | 2 | march 24,2018 | march 25,2018 | [33 empty] | X | X